## Slide 1
Training Effectiveness Agent
L&D Training Effectiveness Report - Technical Leadership & Communication
Evidence gaps block a final effectiveness conclusion.
Blocked
Draft
L&D Manager
Course Leadership_06_2026
6/22/2026, 12:24:18 AM
SETA L&D Reporting

## Slide 2
Executive snapshot
Course Leadership_06_2026
Evidence: Blocked | Draft | L&D Manager
SETA L&D Reporting
Evidence gaps block a final effectiveness conclusion.
The selected scope contains 1 course(s), 0 completed course(s), and 8 trainee-course records. Overall attendance is 47.9%, completion is 0%, pass rate is 0%, and average score is N/A/10. Total training hours are 34.5 and scaled cost is 4.8. Final effectiveness conclusion is blocked because required evidence is incomplete or course status is not completed.
Decision readiness
Blocked
Missing evidence: 1
Warnings: 1
Final conclusion is blocked until required evidence is resolved.
ATTENDANCE
47.9%
Target >= 85%
Risk
COMPLETION
0%
Target >= 90%
Risk
PASS RATE
0%
Target >= 80%
Risk
AVG SCORE
N/A/10
Threshold 6.5
Tracked

## Slide 3
Decision readiness
Course Leadership_06_2026
Evidence: Blocked | Draft | L&D Manager
SETA L&D Reporting
Decision readiness
Blocked
Missing evidence: 1
Warnings: 1
Final conclusion is blocked until required evidence is resolved.
Final conclusion is blocked until required evidence is resolved.
Validated gate checks
Ready
Source availability and required columns
Required sheets and columns were mapped from Teams, OneDrive, Forms, KPI, Rules and Template sources.
Blocked
Course status
1 selected course(s) are not completed.
Warning
Attendance completeness
Expected attendance rows are trainee count x total sessions. Late is retained for metrics as partial attendance.
Ready
Assessment completeness
Completed courses require one valid assessment and pass-status row per trainee.
Ready
Feedback completeness
NORM-14 requires at least 60% feedback response rate for valid analysis.

## Slide 4
Performance scorecard
Course Leadership_06_2026
Evidence: Blocked | Draft | L&D Manager
SETA L&D Reporting
ATTENDANCE
47.9%
Target >= 85%
Risk
COMPLETION
0%
Target >= 90%
Risk
PASS RATE
0%
Target >= 80%
Risk
AVG SCORE
N/A/10
Threshold 6.5
Tracked
SATISFACTION
4.8/5
Target >= 4.0
Good
TRAINING HOURS
34.5
Tracked
Tracked
COST
4.8
Scaled cost
Tracked
ROI PROXY
N/A
Relative KPI
Tracked
Completion is attendance-based (>= 70%) and is intentionally separate from pass rate.

## Slide 5
Course performance
Course Leadership_06_2026
Evidence: Blocked | Draft | L&D Manager
SETA L&D Reporting
Course | Learners | Attend. | Complete | Pass | Score | Effectiveness
Technical Leadership & Communic... | 8 | 47.9% | 0% | 0% | N/A/10 | 25.58
What to notice
Strong completion outcome at 0%
Overall effectiveness score is 25.58
Technical Leadership & Communication has an effectiveness score of 25.58 in the selected scope.

## Slide 6
Key findings and implications
Course Leadership_06_2026
Evidence: Blocked | Draft | L&D Manager
SETA L&D Reporting
Risk
Strong completion outcome at 0%
Evidence: Completion is calculated as attendance >= 70%; pass rate is tracked separately at 0%.
Implication: Learners are completing the required session exposure, and assessment achievement is also healthy.
Risk
Overall effectiveness score is 25.58
Evidence: Attendance 47.9%, pass rate 0%, average score N/A/10.
Implication: The selected scope is classified as Not reportable.
Good
Technical Leadership & Communication has an effectiveness score of 25.58 in the selected scope.
Evidence: Supported by validated metrics, evidence gate, and L&D NORM checks.
Implication: Use this signal to prioritize follow-up actions and stakeholder communication.
Monitor
1 course group contained learners who need support based on score or attendance policy.
Evidence: Supported by validated metrics, evidence gate, and L&D NORM checks.
Implication: Use this signal to prioritize follow-up actions and stakeholder communication.

## Slide 7
Evidence traceability
Course Leadership_06_2026
Evidence: Blocked | Draft | L&D Manager
SETA L&D Reporting
Every narrative claim is backed by validated artifacts before export.
Ready
Source availability and required columns
Required sheets and columns were mapped from Teams, OneDrive, Forms, KPI, Rules and Template sources.
Blocked
Course status
1 selected course(s) are not completed.
Warning
Attendance completeness
Expected attendance rows are trainee count x total sessions. Late is retained for metrics as partial attendance.
Ready
Assessment completeness
Completed courses require one valid assessment and pass-status row per trainee.
Ready
Feedback completeness
NORM-14 requires at least 60% feedback response rate for valid analysis.
Ready
Row-level data quality
Duplicate rows and numeric ranges were checked before metric generation.

## Slide 8
Governance and access
Course Leadership_06_2026
Evidence: Blocked | Draft | L&D Manager
SETA L&D Reporting
CLASSIFICATION
Not reportable
SENSITIVE DETAILS
Visible
RAW APPENDIX
Allowed
HIGH-PRIORITY FLAGS
10
High
NORM-01 | High
Pass rate is below 70%.
Medium
NORM-03 | Medium
Attendance rate is below 75%.
High
NORM-05 | High
Trainee has zero score or missing assessment.
High
NORM-05 | High
Trainee has zero score or missing assessment.

## Slide 9
Recommended action plan
Course Leadership_06_2026
Evidence: Blocked | Draft | L&D Manager
SETA L&D Reporting
1
Medium
Team Manager + L&D
Flag course for content review; notify L&D manager
Improve training effectiveness and repeatability.
2
High
L&D Manager
Mark as Incomplete; recommend re-enrollment in next cohort
Improve training effectiveness and repeatability.
3
High
L&D Manager
Block final conclusion; flag data incomplete
Improve training effectiveness and repeatability.
4
High
L&D Manager
Do not publish a final effectiveness conclusion until blocked evidence items are resolved.
Improve training effectiveness and repeatability.
5
Low
L&D Manager
Use this output as a preliminary readiness report and assign owners to missing evidence items.
Improve training effectiveness and repeatability.

## Slide 10
Delivery roadmap
Course Leadership_06_2026
Evidence: Blocked | Draft | L&D Manager
SETA L&D Reporting
Step 1
Medium
Team Manager + L&D
Flag course for content review; notify L&D manager
Expected outcome
Improve training effectiveness and repeatability.
Step 2
High
L&D Manager
Mark as Incomplete; recommend re-enrollment in next cohort
Expected outcome
Improve training effectiveness and repeatability.
Step 3
High
L&D Manager
Block final conclusion; flag data incomplete
Expected outcome
Improve training effectiveness and repeatability.
Step 4
High
L&D Manager
Do not publish a final effectiveness conclusion until blocked evidence items are resolved.
Expected outcome
Improve training effectiveness and repeatability.

## Slide 11
Appendix and methodology
Course Leadership_06_2026
Evidence: Blocked | Draft | L&D Manager
SETA L&D Reporting
Source traceability
Report ID: rpt_c549e4e5-1c97-4658-9530-f4e846e8cf9d
Dataset ID: ds_083aa17e722e3088
Metrics snapshot ID: mx_ccf25979-0718-4cf9-90c8-7ef4d329d668
Evidence decision ID: ev_94d9a5bb-9fb8-4264-aa09-e3b0d7c470e2
Governance view ID: gv_b4699339-7ed7-4550-a8e6-ef738c1fd59d
Role view: L&D Manager
Sensitive details: visible
LLM disclosure
Deterministic fallback used. OPENAI_API_KEY is not configured or LD_REPORTING_USE_LLM=false.
Business rule
Completion rate is calculated from learner attendance >= 70%. Pass rate is calculated independently from assessment pass status.